## Pr08-93
Activity |  |  |  | Expected Completion Time (Days) | Variance
Develop survey questionnaire |  |  |  | 10 | 2
Pretest the questionnaire |  |  |  | 11 | 7
Revise the questionnaire |  |  |  | 5 | 2
Hire survey company |  |  |  | 2 | 1
Conduct survey analyze data |  |  |  | 30 | 9
Analyze data |  |  |  | 32 | 11
Prepare report |  |  |  | 13 | 4
Let X represent the time to launch the new product.
Event 1: X more than | 109 | days
Event 2: X more than | 95 | days
Event 3: X between | 96 | and | 113 | days